## Project Planner
Sydney Airbnb Database Analysis
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 32 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Initiation
1.1 Review the dataset | 1 | 5 | 2 | 7 | 100%
1.2 Gather feature requirements | 2 | 10 | 3 | 9 | 100%
1.3 Assign tasks | 3 | 4 | 3 | 6 | 100%
1.4 Prepare relevant tools and materials | 10 | 7 | 12 | 7 | 100%
2. Planning
2.1 Project Plan Development
2.1.1 Scope Statement | 13 | 7 | 13 | 8 | 100%
2.1.2 WBS and schedule | 13 | 7 | 13 | 6 | 100%
2.2 Software Design Development
2.2.1 Define user requirements | 14 | 6 | 15 | 5 | 100%
2.2.2 Define software requirements | 16 | 5 | 16 | 5 | 100%
2.2.3 Use cases | 17 | 6 | 17 | 7 | 100%
2.2.4 System components | 19 | 11 | 20 | 12 | 100%
2.2.5 Graphics & interface planning | 22 | 10 | 23 | 10 | 100%
3. Executing
3.1 Data analysis
3.1.1 Data cleaning & preprocessing | 33 | 5 |  |  | 0%
3.1.2 Data sorting & info extraction | 37 | 3 |  |  | 0%
3.1.3 Exploratory Data Analysis | 38 | 6 |  |  | 0%
3.2 GUI Implementation
3.2.1 Create interface | 38 | 10 |  |  | 0%
3.2.2 Database integration | 42 | 6 |  |  | 0%
3.2.3 Data Insight Visualization | 46 | 5 |  |  | 0%
3.3 Requirements Acceptance Testing | 50 | 11 |  |  | 0%
4. Controlling
4.1 Status reports | 1 | 60 |  |  | 0%
4.2 Update plans and schedule | 43 | 18 |  |  | 0%
5. Closing
5.1 Lesson learned | 52 | 3 |  |  | 0%
5.2 Prepare final report | 52 | 9 |  |  | 0%